## Sheet1
Date | priority | name | Date Started | Date Finished | Discription | Hours Est | Hours Act | Notes
2013-06-07 | a | Text Scrolling | 2013-06-06 | 2013-06-07 | Not sure how to handle it if they ship more than one line except to create a new screen | n/a | 8 | Changed the template to include formatting and settings
2013-06-07 |  | Future Date |  |  | The reporting, we need to be able to filter The date filters – they shouldn’t be able to pick a date a month later than the current date
2013-06-07 |  | Replacement Part Field |  |  | We would like to add a field to input the replacement parts used to fix a current unit Something like: Internal replacement part Internal replacement part description Internal replacement SN
2013-06-07 |  | Repair Date Field |  |  | We are being asked to have a field called Repair date
2013-06-07 |  | RoC Field |  |  | We are being asked on the Product Dispostion field to add “Return to Customer”
2013-06-07 |  | Delete Duplicates |  |  | Is there a way for them to delete duplicate records?
2013-06-07 |  | Selective Editing |  |  | Is there a way for them to edit certain fields?
2013-06-07 |  | Direct Updating |  |  | I also have a facility asking if they upload from their system into the portal so they don’t have to duplicate the information